## Process Data
N° | Stage | Step | Input fields or cluster | Output fields or cluster | R | A | C | I
1 | 1 | Review Market | Idea description | Market review report | PM or AM
2 | 1 | Review Portfolio | Idea description | Portfolio Review report | PM or AM
3 | 1 | Perform Competitive Analysis | Idea description | Competitor Analysis Report | PM or AM
4 | 1 | Analyzing underlying problem/opportunity/threat | * Idea description * Market review report * Competitor Analysis report * Portfolio Review report | Problem Canvas | PM or AM
5 | 1 | Define Mission, Goals and Objectives | problem canvas | Mission One Pager | PM or AM
6 | 1 | Estimate Project Size, Impact and Strategic Fit | *Mission Statement *Business Goals *Customer Goals *Business Objectives *Business Goals | Project Estimation | PM or AM
7 | 1 | Define High Level Risks | Mision One Pager Project Estimation | List of Major Risks | PM or AM
8 | 1 | Estimate resources to MAP project | Mision One Pager Project Estimation | *type of ressources *ressources usage | PM or AM
9 | 1 | Allocate team members for MAP project | *type of ressources *ressources usage | Ressources allocation | Head of assigned ressources
10 | 1 | Estimate MAP Project Duration | *Mision One Pager *Project Estimation *ressources allocation | MAP lead time | PM or AM
11 | 1 | ONE PAGER TEMPLATE COMPLETED | *Problem Statement *Mission Statement *Business Goals *Customer Goals *Business Objectives *Customer Objectives *Project Size *Impact *Startegic Fit | One Pager Template | AUTOMATIC
12 | 1 | Elaborate MAP Project Charter | *Mission Statement *Business Goals *Customer Goals *Business Objectives *Customer Objectives *List of Major Risks *ressources allocation *MAP lead time | MAP Project Charter template | AUTOMATIC
13 | 1 | Rate MAP project (Stage 1) | One Pager Template MAP Project Charter | MAP project rating | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)
14 | 1 | Gate 1 decision | MAP project rating | Approval for moving to Stage 2 OR Rejection | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)
| 2 | Identify Stakeholders | One Pager Template | Stakeholder | PM or AM
| 2 | Characterize Persona | Stakeholder | Persona
| 2 | Elicit Stakeholder Needs | Stakeholder Persona | Needs elicitation outcome | PM or AM
| 2 | Formulate and document Stakeholder Needs | Needs elicitation outcome | *Need Statement *Originator/Author *Owner *Priority *Criticality *Rationale/Reason Why *Allocation / Budgeting *trace to source
| 2 | Identify Drivers & Constraints | One Pager Template | Drivers & Constraints | PM or AM
| 2 | Identify Stakeholders related to Drivers&Constraints (if any)​ | Drivers & Constraints | Stakeholder | PM or AM
| 2 | Formulate needs related to these Drivers & Constraints and document them | Drivers & Constraints Stakeholder | *Need Statement *trace to source *Originator/Author *Owner *Criticality *Rationale/Reason Why *Allocation / Budgeting | PM or AM
| 2 | Identify Conflicting Needs | * Need Statement *Originator/Author *Owner *Criticality *Rationale/Reason Why *Allocation / Budgeting | * Conflicting Needs link * Conflicting needs rational | PM or AM
| 2 | Conduct Risks Assessment Stage 2 | *Need Statement *Originator/Author *Owner *Criticality *Rationale/Reason Why *Allocation / Budgeting *Conflicting needs rational *trace to source | Risk Identification | PM or AM
| 2 | Rate MAP project (Stage 2) | *Need Statement *Originator/Author *Owner *Priority *Criticality *Rationale/Reason Why *Allocation / Budgeting *Conflicting needs link *Conflicting needs rational *Risk Identification | MAP project rating | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)
| 2 | Gate 2 decision | MAP project rating | Approval for moving to Stage 2 OR Rejection | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)

## Fields
Field ID | Cluster | Field Name | Type | Description | Possible Values | Check Criteria | Related Stage
1 | Idea description | Type of idea | selection |  | new application, new product, maintenance solution, technology push, cross | MUST | 1
2 | Idea description | Impact on portfolio | selection | Are there specific *applications/products/components affected by your idea? | portfolio of applications, products. Open for components | MUST | 1
3 | Idea description | Brand | selection | Does the idea affect Unit A, Unit B or both brands? | Unit A, Unit B, both | OPTIONAL | 1
| Idea description | Idea description | text | What is your idea and what chance does it offer?​ |  | MUST | 1
| Idea description | Reason why | text | Why does the chance exist? What is the underlying problem? Why is the opportunity there? |  | MUST | 1
| Idea description | Target audience | text | Who has the problem the most often? |  | MUST | 1
| Idea description | Status quo | text | Describe the current situation: What are the customer currently doing and what shortcomings are they facing?​​ |  | MUST | 1
| Idea description | Review status | selection |  | submitted - in review - accepted - declined |  | 1
| Idea description | Review comment | text |  |  | MUST | 1
| Market Review | Market review report | document | this document should cover: *trend of relevant technologies in the market*How the idea is unique, radical or cutting-edge in the market*Customer Paint Points*Forthcoming trends regarding products, technologies,... |  | optional | 1
| Portfolio Review | Portfolio Review Report | document | A report that identify what is the gap/need in the current portfolio |  | optional | 1
| Competitor Analysis | Competitor Analysis Report | document | A report on competitors including the name of competitors, their relevant products, the technical features of their product(s), the picture of their product(s), the price, etc. |  | optional | 1
| Problem Canvas | Root cause | text | Explain why the problem exists at all. |  | MUST | 1
| Problem Canvas | Customer | text | Who has the problem the most often? |  | MUST | 1
| Problem Canvas | Current situation | text | What is the customer currently doing and what are the faced shortcomings?​ |  | MUST | 1
| Problem Canvas | Problem statement | text | Summarize the problem in a concise problem statement with less than 150 words. |  | MUST | 1
| Mission One pager | Mission Statement | text | Define a compelling statement explaining what the system will do and the purpose of doing it in less than 150 words. It should provide clarity both internally and externally by simply answering the following questions: What will the project will do (its outcome)? Why does the project exist? When should the project be on the market? Where does the project will be sold? Who is our customers? The How is optional. |  | MUST | 1
| Mission One pager | Business Goals | text | Define 2-4 statements of what our business needs to achieve to fulfill the mission statement. Goals are single, concise statements starting with an action verb expressed in qualitative terms, e.g. increase profitability. |  | MUST | 1
| Mission One pager | Customer Goals | text | Define 2-4 statements of what our customers hope to achieve in the context of the mission statement. Goals are single, concise statements starting with an action verb expressed in qualitative terms, e.g. reduce maintenance efforts. |  | MUST | 1
| Mission One pager | Business Objectives | text | For each goal, formulate up to seven statements that outline what must be achieved to reach the goal. Upon project completion, the objectives must be approved to confirm that the goals and mission have been fulfilled. Therefore, objectives could encompass key deliverables and are often expressed in quantitative terms, such as a 40% profit per unit. |  | MUST | 1
| Mission One pager | Customer Objectives | text | For each goal, formulate up to seven statements that outline what must be achieved to reach the goal. Upon project completion, the objectives must be approved to confirm that the goals and mission have been fulfilled. Therefore, objectives could encompass key deliverables and are often expressed in quantitative terms, such as a 40% profit per unit. |  | MUST | 1
| Project Estimation | Project Size/ Effort estimation | selection | XS = XS projects are characterized by their minimal complexity and innovation. They typically involve straightforward tasks, routine maintenance, or small-scale updates to existing applications, products, or services. XS projects are quick to complete and require minimal resources. XL = XL projects are at the highest end of the scale in terms of complexity and innovation. They involve groundbreaking initiatives, disruptive innovations, or the development of entirely new markets, industries, or product families. XL projects are ambitious and often require extensive resources, long-term commitments, and substantial risk-taking. | XS - S - M - L - XL | MUST | 1
| Project Estimation | Project Size/ Effort estimation justification | text | Provide rational for your selection |  | MUST | 1
| Project Estimation | Strategic fit | selection | Low Strategic Fit = The system deviates significantly from the brand's identity, values, or positioning, potentially causing brand inconsistency or dilution. The system may not be closely tied to the organization's overarching strategic objectives, potentially resulting in suboptimal use of resources. The system may struggle to support the achievement of sales targets in various regions, due to a lack of adaptability or relevance. High Strategic Fit = The system fully embraces and reinforces the organization's brand identity, values, messaging, and positioning. It enhances brand equity, consistency, and recognition. The system is a key driver of the organization's broader strategic goals and objectives. It directly contributes to the execution of strategic initiatives, improves competitiveness, and fuels growth. The system effectively supports and enables the achievement of specific sales targets set by individual countries or regions where the organization operates. It adapts seamlessly to local market dynamics. | Low - Moderate - High | MUST | 1
| Project Estimation | Strategic fit justification | text | Explain how the system is aligned with brands and XXX Group Strategies. Consider the alignment with sales countries-owned targets. |  | MUST | 1
| Project Estimation | Impact | selection | Low Impact = Low impact projects typically have a minimal influence on the market, or the organization's overall strategic position. They may not significantly affect revenue or brand positioning and do not show any significant differentiation from competitors. High Impact = High impact projects are game-changers, capable of transforming markets or entire industries. They serve as door openers for numerous other projects or markets and have a profound influence on revenue, brand positioning, and differentiation from competitors. | Low - Moderate - Significant - High | MUST | 1
| Project Estimation | Impact justification | text | Explain the impact of the system. Consider its success on the market, if it is a niche market, a door opener to other projects, its estimated revenue for the organization, its influence on the positioning of the brands on the market and its differentiation with competitors. |  | MUST | 1
| Project Charter | List of Major Risks | text | Formulate factors that potentially negatively impact the undertaking. Consider factors such as market situation, development efforts / system complexity, available internal knowledge, organization maturity, legal and regulatory situation |  | MUST | 1
| MAP resources | Type of resources | selection | list all roles needed to run the MAP project | active directory | MUST | 1
| MAP resources | Resource usage | number | estimate the extent you need a specific role. Rely on predefined values if possible |  | MUST | 1
| MAP resources | Resource allocation | selection | assign team members to the listed resources. |  | MUST | 1
| MAP Duration | MAP lead time | selection | Estimate the lead time of the MAP project |  | MUST | 1
| One Pager Template | One Pager Template | automated generated document | Template reporting the different fields: *Problem Statement *Mission Statement *Business Goals *Customer Goals *Business Objectives *Customer Objectives *Project Size *Impact *Startegic Fit
| MAP Project Charter Template | MAP Project Charter | automated generated document | Template reporting the different fields: *Mission Statement *Business Goals *Customer Goals *Business Objectives *Customer Objectives *List of Major Risks *ressources allocation *MAP lead time
| MAP Project Rating Gate 1 | Innovation and Creativity | Selection | assess the level of innovation and creativity demonstrated by the underlying idea. Very High = The idea proposes unconventional, radical, and out-of-the-box solution that challenge established norms, leading to exceptional results. Very Low = The idea lacks originality and innovation, resembling commonly seen concepts | Very High - High - Medium - Low - Very Low | MUST | 1
| MAP Project Rating Gate 1 | Innovation and Creativity Justification | text |  |  | OPTIONAL | 1
| MAP Project Rating Gate 1 | Alignment with Strategic Objectives | Selection | evaluate how well each idea aligns with the strategic goals and objectives of the organization Very high = The idea perfectly aligns with all strategic objectives, contributing significantly to key performance indicators and growth targets. Very low = The idea lacks clear alignment with the company's strategic objectives, offering minimal support to important goals. | Very High - High - Medium - Low - Very Low | MUST | 1
| MAP Project Rating Gate 1 | Alignment with Strategic Objectives Justification | text |  |  | OPTIONAL | 1
| MAP Project Rating Gate 1 | Market Demand and Potential | Selection | evaluate if the idea address a clear market need or opportunity. It should have the potential to meet customer demands, solve a problem, or create value in the market. Very high = There's strong evidence of high demand and potential. Very low = The idea has minimal to no market demand or potential. | Very High - High - Medium - Low - Very Low | MUST | 1
| MAP Project Rating Gate 1 | Market Demand and Potential Justification | text |  |  | OPTIONAL | 1
| MAP Project Rating Gate 1 | Competitive Advantage | Selection | evaluate the competitive advantage or uniqueness that the idea offers. Very high = The idea possesses exceptional competitive advantages that give it a significant edge over competitors. It's difficult for others to replicate or counter these advantages. very low = The idea lacks significant competitive advantages, and its differentiation from competitors is minimal. | Very High - High - Medium - Low - Very Low | MUST | 1
| MAP Project Rating Gate 1 | Competitive Advantage Justification | text |  |  | OPTIONAL | 1
| MAP Project Rating Gate 1 | Level of Risk (1) | Selection | evaluate the potential risks and challenges associated with implementing the idea. Very high = The idea is associated with numerous high-impact and highly likely risks that could significantly impede its success. Very low = The idea has minimal to no significant risks that could jeopardize its success. | Very High - High - Medium - Low - Very Low | MUST | 1
| MAP Project Rating Gate 1 | Risk Stage 1 Justification | text |  |  | OPTIONAL | 1
| MAP Gate 1 Decision | MAP project approval | selection |  | Yes - No | MUST | 1
| MAP Gate 1 Decision | MAP project approval justification | text |  |  | OPTIONAL | 1
| Stakeholder | Stakeholder Name | text | Name the stakeholder |  | MUST | 2
| Stakeholder | Stakeholder Description | text | Describe in few words the main characteristics of the stakeholder |  | MUST | 2
| Stakeholder | Stakeholder Internal/External | selection |  | Internal, External | MUST | 2
| Stakeholder | Stakeholder Involvment | selection | How important is the stakeholder for our mission ? | Vested, Influence, Participate | MUST | 2
| Stakeholder | Stakeholder Lifecycle Stages | multi selection | In what lifecycle stage(s) is the stakeholder participating? Possibility to choose 1 or more. | Glossary_Lifecycle | MUST | 2
| Persona | Persona Name | text | Give the specific persona a title that makes it more specific than the generic stakeholder description. |  | OPTIONAL | 2
| Persona | Persona Description | text | Elaborate on the persona in order to clearly describe the demographic, the skill level etc. |  | OPTIONAL | 2
| Persona | Persona brand Attitude | selection | What is the experience of the persona with our brands? | Promoter, Neutral, Detractor | OPTIONAL | 2
| Persona | Corpration Size | selection | For professional partners, please indicate the size of the company they are employed by. Small <50 employees Medium < 250 employees Large >250 employees | Small, Medium, Large | OPTIONAL | 2
| Persona | Application Expertise | Selection | How much experience does the stakeholder bring in relation to our target application? High - daily business Medium - often confronted Low - once in while | High, Medium, Low | OPTIONAL | 2
| Persona | Age Range | selection | Point out the demographics of the persona. Age range is sufficient. | >18 18-30 31-40 41-50 51-60 <30 | OPTIONAL | 2
| Persona | Contact Aquisition | text | Point out how the stakeholder should be contacted. Does our sales organization have established contacts? If not: how should we make contact with potential stakeholders? |  | OPTIONAL | 2
| Persona | contact Information | text | If the stakeholders is directly contacted, please specify his relevant contact information (email, phone number,etc) |  | OPTIONAL | 2
| Needs | Needs elicitation outcome | document | Upload the documentation of your needs elicitation. Please upload all relevant data, trancriptions, presentations etc. |  | OPTIONAL | 2
| Needs | Needs Category | selection | Function : The action(s) that the system needs to perform. Function includes functionality and associated performance. The functions address the features the stakeholder expect thesystem to have, performance addresses how well, how many, how fast, etc. attributes of a function. Fit: The ability of the system to interface with, interact, connect to, operate, and become an integral part of the macro system it is a part of. “Fit” includes human system interactions and interfaces as well as both the induced and natural environments (conditions of operations, transportation, storage, maintenance). Form: The shape, size, dimensions, mass, weight and other visual parameters that uniquely distinguish a system. “Form” addresses the physical nature of the system. For software “form” could address programming language, lines of code, memory requirements, etc. Quality: Fitness for use (safety, security, and various quality “ilities”, e.g., reliability, testability, operability, availability, maintainability, operability, supportability, manufacturability, interoperability, safety, security, to name a few. Compliance: Satisfying design and construction standards and regulations | Function, Fit, Form, Quality, Compliance | MUST
| Needs | Need Statement | text | A need stating the need of a stakeholder or a persona follwing this formulation:"The [stakeholders] need the system to….". This need is formulated based on a source (interviews, surveys, …) |  | MUST | 2
| Needs | Originator/Author | text | The person defining and entering a need |  | MUST | 2
| Needs | Owner | text | The person or organizational element that maintains the need , who has the right to say something about this need , approves changes to the need , and reports the status of the need . Per default, you are the owner. Yet, please do not forget about our standards & regulations team. |  | OPTIONAL | 2
| Needs | Criticality | selection | A critical or essential need is one that the product/services/controls must achieve to function at all | Must, Should, Could | MUST | 2
| Needs | Rationale/Reason Why | text | Rationale defines why the need should be included and other information relevant to better understand the reason for and intent of the need. |  | MUST | 2
| Needs | allocation / budgeting | text | Is the need related to this product only or is it related to another system / plattform? |  | OPTIONAL | 2
| Needs | Need Verification Status: : Need meets internal guidelines | selection | An indication that a need has been verified. is the need written according to the internal guideline? | to be verified, verified and to be modified,verified and approved | MUST | 4
| Needs | Need Verification Status: comment | text | comment for the verification status "verified and to be modified" : explain why the needs should be modified and make a modification proposal |  | MUST | 4
| Needs | Need Validation Status: need(s) makes sense and is feasible | selection | An indication the need or requirement has been validated. | to be validated, be corrected ,validated | MUST | 4
| Needs | Need Validation Status: comment | text | comment on the validation status " to be corrected": describe the reason why |  | MUST | 4
| Needs | System Validation success criteria | text | The criteria that must be met to provide sufficient evidence that a product/service/control system has successfully met a need as defined by the strategy and method used to validate it. |  | MUST | 4
| Needs | System Validation Strategy | text | What is the strategy to ensure that a product/service/control system meets a need ? |  | MUST | 4
| Needs | System Validation Method | text | The Validation Method for each need states the planned Method to be used (Test, Demonstration, Inspection, Analysis) to provide the evidence that the product/service/control system meets the success criteria |  | MUST | 4
| Needs | Risk - Need Attribute | selection | A value assigned to each need indicating the risk of the need not being met (according to the feasibility of the need). | high, medium, low | MUST | 4
| Needs | trace to parent | link | A child need is a need that has been derived or decomposed from a parent need. The trace is a link from the child to parent. |  | OPTIONAL | 2
| Needs | trace to source | link | Each need must be linked to a source to establish where the need was derived from. Examples of sources include mission, goals, or objectives, minutes of stakeholder workshop, interviews, analysis, documents, regulations, standards, risk, derived from a trade study,... |  | MUST | 2
| Needs | Trace to Dependent Stakeholder Needs | link | Link between stakeholder needs that are related to or dependent on each other at the same level (no parent-child linked!) |  | OPTIONAL | 2
| Needs | Conflicting needs link | Link | Identify andlink the conflicting needs together ( |  | OPTIONAL | 2
| Needs | Conflicting needs rational | text | Explain in the comment why this is a conflicting need |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Application Standards | text | Identify any legal or regulatory constraints that may apply to the products/controls/services |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Countries Regulations | text | Identify any legal or regulatory constraints that may apply to the products/controls/services |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Other Regulations | text | Identify any legal or regulatory constraints that may apply to the products/controls/services |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Compatibility with other products/control systems | text | With which existing systems, our system is interacting during each lifecycle stages ? |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Natural Environment | text | In which environment (temperature, humidity) will the product be installed ? This may later drive the choice of materials for example. |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Human/System Interface | text | With what kind of user our product/control system will interact ? Think about User skills, user accessibility, user languages |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Internal Strategy (Group, Brands,…) | text | List Group/Brands Strategy/ Goals that can be significant drivers for our system |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Sustainability | text | Is there any sustainability strategy that will constraints or drive the development of our products/control system that we can already identified at this stage ?
| Drivers & Constraints | D&C - Sustainability_Circular Design Rules | text | What are the constraints related to CDR to achieve the target ? |  | OPTIONAL | 2
| Drivers & Constraints | D&C - New technologies | text | Available new technologies on the market to take into account |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Competitor trends | text | Available competitor innovation on the markets that can influence the future development of our products |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Budget | text | Is there any budget constraints that need to be taken into account at this stage ? Ex: system needs to be cheaper as competitor XX |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Budget | document |  |  | OPTIONAL | 2
| Drivers & Constraints | D&C - Schedule | text | Is there any schedule constraints that need to be taken into account at this stage ? Ex: system needs to be launched before XXX |  | OPTIONAL | 2
| Risk register | Risks Identification | text | add your concerns regarding the mission and related needs: what are the risks that should be taken into account? |  | MUST | 2
| MAP Project Rating Gate 2 | Needs Elicitation Approach | Selection | evaluate how well and complete the stakeholders’ needs have been understood.​ Very High = An exceptional effort has been demonstrated in the needs elicitation. Every single stakeholder with potential interest or involvement in the project has been proactively contacted and engaged with. By including every stakeholder, even those indirectly affected, a comprehensive understanding of all perspectives and requirements is assured. This leads to achieving a high level of stakeholder satisfaction and alignment with the project's objectives.​ Very Low= Minimal or no effort has been made to contact stakeholders for needs elicitation. There is little to no engagement with stakeholders, and consideration for gathering input from those who could impact or be impacted by the project is lacking. This approach could result in severe disconnects between project objectives and stakeholder expectations, potentially leading to project failure or dissatisfaction.​ | Very High - High - Medium - Low - Very Low | MUST | 2
| MAP Project Rating Gate 2 | Needs Elicitation Approach justification | text |  |  | OPTIONAL | 2
| MAP Project Rating Gate 2 | Conflicting needs Rating | Selection | evaluate how critical conflicting needs are and how easy they can be handled.​ Very high = Conflicting needs among stakeholders have meticulously identified, documented, and categorized, ensuring a comprehensive understanding.​ Very low = The identification and documentation of conflicting needs among stakeholders is poor, raising concerns about potential disputes.​ | Very High - High - Medium - Low - Very Low | MUST | 2
| MAP Project Rating Gate 2 | Conflicting needs rating justification | text |  |  | OPTIONAL | 2
| MAP Project Rating Gate 2 | Drivers & Constraints | Selection | assesse how helpful drivers are and how difficult constraints are to manage. ​ Very High = The idea is backed by highly beneficial drivers that strongly contribute to its success, and the constraints are extremely manageable, requiring minimal effort to overcome.​ Very Low = The idea is backed by highly beneficial drivers that strongly contribute to its success, and the constraints are extremely manageable, requiring minimal effort to overcome.​ | Very High - High - Medium - Low - Very Low | MUST | 2
| MAP Project Rating Gate 2 | Drivers & Constraints justification | text |  |  | OPTIONAL | 2
| MAP Project Rating Gate 2 | Level of Risk (2) | Selection | evaluate the potential risks and challenges associated with implementing the idea. Very high = The stakeholders’ needs are associated with numerous high-impact and highly likely risks that could significantly impede its success.​ Very low = The stakeholders’ needs have minimal to no significant risks that could jeopardize its success. | Very High - High - Medium - Low - Very Low | MUST | 2
| MAP Project Rating Gate 2 | Risk Stage 2 Justification | text |  |  | OPTIONAL | 2
| MAP Gate 2 Decision | MAP project approval gate 2 | selection |  | Yes - No | MUST | 2
| MAP Gate 2 Decision | MAP project approval justification | text |  |  | OPTIONAL | 2

## Glossary_Lifecycle
Term | Definition
Concept Stage | The phase where initial ideas and high-level plans for a SOI are generated and evaluated using the MAP process
Development | The process of turning conceptual designs into a tangible SOI through design, engineering /implementation, and manufacturing planning using the PCP.
Manufacturing | Transforming the product's design and specifications into a tangible physical product through processes such as production, assembly, quality control, and distribution.
Verification | The systematic assessment of a SOI to ensure it meets specified requirements and standards.
Validation | The process of evaluating a SOI's performance and functionality to ensure it meets user needs and expectations.
Planning Lighting
Order Phase
Shipping
Operation | The period during which a SOI is actively used and performs its intended functions. Commonly, multiple lifecycle stage scenarios are used to differentiate operation modes, e.g. "luminaire on", "luminaire off", "luminaire standby"
Launch | the introduction of a SOI to the market, making it available for purchase and use by customers.
Sales | The activity of attracting potential customers to the SOI, exchanging the SOI for payment, involving transactions between the seller and the customer.
Installation&Commissioning | The process of setting up and initiating a SOI's operation in its intended environment.
On-site Maintenance | The ongoing activities aimed at keeping a SOI in good working condition while it is in use, typically performed at the product's location.
Remanufacturing | The comprehensive process of disassembling, repairing, and rebuilding a used SOI to bring it back to a "like-new" state.
Refurbishment | The process of improving or renovating a SOI's condition, functionality, or appearance to extend its useful life.
End of life | The stage when the SOI is no longer in use, either due to obsolescence or the completion of its intended lifecycle, and it may be disposed of or recycled.