## Process Data_Cleaned
N° | Stage | Step | Input fields or cluster | Output fields or cluster | R | A | C | I
1 | 1 | Review Market | Idea description | Market review report | PM or AM
2 | 1 | Review Portfolio | Idea description | Portfolio Review report | PM or AM
3 | 1 | Perform Competitive Analysis | Idea description | Competitor Analysis Report | PM or AM
4 | 1 | Analyzing underlying problem/opportunity/threat | Idea description Market review report Competitor Analysis report Portfolio Review report | Problem Canvas | PM or AM
5 | 1 | Define Mission, Goals and Objectives | problem canvas | Mission One Pager | PM or AM
6 | 1 | Estimate Project Size, Impact and Strategic Fit | Mission One Pager | Project Estimation | PM or AM
7 | 1 | Define High Level Risks | Mission One Pager Project Estimation | Project Charter | PM or AM
8 | 1 | Estimate resources to MAP project | Mision One Pager Project Estimation | *type of ressources *ressources usage | PM or AM
9 | 1 | Allocate team members for MAP project | *type of ressources *ressources usage | *ressources allocation | Head of assigned ressources
10 | 1 | Estimate MAP Project Duration | Mision One Pager Project Estimation *ressources allocation | MAP Duration | PM or AM
11 | 1 | ONE PAGER TEMPLATE COMPLETED | Problem Canvas Mission One Pager Project Estimation | One Pager Template | AUTOMATIC
12 | 1 | Elaborate MAP Project Charter | Mission One Pager Project Charter *ressources allocation MAP Duration | MAP Project Charter | AUTOMATIC
13 | 1 | Rate MAP project (Stage 1) | One Pager Template MAP Project Charter | MAP project rating gate 1 | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)
14 | 1 | Gate 1 decision | MAP project rating gate1 | Approval for moving to Stage 2 OR Rejection | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)
| 2 | Identify Stakeholders | One Pager Template | Stakeholder | PM or AM
| 2 | Characterize Persona | Stakeholder | Persona
| 2 | Elicit Stakeholder Needs | Stakeholder Persona | Needs elicitation outcome | PM or AM
| 2 | Formulate and document Stakeholder Needs | Needs elicitation outcome | *Need Statement *Originator/Author *Owner *Priority *Criticality *Rationale/Reason Why *Allocation / Budgeting *trace to source
| 2 | Identify Drivers & Constraints | One Pager Template | Drivers & Constraints | PM or AM
| 2 | Identify Stakeholders related to Drivers&Constraints (if any)​ | Drivers & Constraints | Stakeholder | PM or AM
| 2 | Formulate needs related to these Drivers & Constraints and document them | Drivers & Constraints Stakeholder | *Need Statement *trace to source *Originator/Author *Owner *Criticality *Rationale/Reason Why *Allocation / Budgeting | PM or AM
| 2 | Identify Conflicting Needs | * Need Statement *Originator/Author *Owner *Criticality *Rationale/Reason Why *Allocation / Budgeting | * Conflicting Needs link * Conflicting needs rational | PM or AM
| 2 | Conduct Risks Assessment Stage 2 | *Need Statement *Originator/Author *Owner *Criticality *Rationale/Reason Why *Allocation / Budgeting *Conflicting needs rational *trace to source | Risk Identification | PM or AM
| 2 | Rate MAP project (Stage 2) | *Need Statement *Originator/Author *Owner *Priority *Criticality *Rationale/Reason Why *Allocation / Budgeting *Conflicting needs link *Conflicting needs rational *Risk Identification | MAP project rating | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)
| 2 | Gate 2 decision | MAP project rating | Approval for moving to Stage 3 OR Rejection | VP Zumtobel Brand & Application VP Brand & Application Thorn (others tbd)