Stage 1 — Dependency Description

Stage 1 consists of a sequence of activities connected by explicit input-output dependencies. Each artifact is produced by exactly one activity and may be used as input by later activities.

The stage begins with three independent activities that can be executed in parallel:

- Review Market, producing the Market Review report

- Review Portfolio, producing the Portfolio Review report

- Perform Competitive Analysis, producing the Competitor Analysis report

All three activities use the Idea description as their input.

Once these three reports are available, the activity Analyzing underlying problem/opportunity/threat starts. This activity requires the Market Review report, Portfolio Review report, and Competitor Analysis report, and produces the Problem Canvas.

The Problem Canvas is then used by Define Mission, Goals and Objectives, which produces the Mission One Pager.

The Mission One Pager is used by Estimate Project Size, Impact and Strategic Fit, which produces the Project Estimation.

After the Project Estimation becomes available, three activities may start:

- Define High Level Risks, which produces the Project Charter

- Estimate resources to MAP project, which produces MAP Resources I

- Complete the One Pager Template, which uses Problem Canvas, Mission One Pager, and Project Estimation, and produces the One Pager Template

When MAP Resources I is produced, the activity Allocate team members for MAP project starts and produces MAP Resources II.

Once MAP Resources II is available, the activity Estimate MAP Project Duration starts. This activity also requires Mission One Pager and Project Estimation, and produces the MAP Duration.

The activity Elaborate MAP Project Charter can start only after all of the following artifacts are available:

- Mission One Pager

- Project Charter

- MAP Resources II

- MAP Duration

This activity produces the MAP Project Charter.

The activity Rate MAP project (Stage 1) requires the One Pager Template and the MAP Project Charter, and produces the MAP Project Rating Gate 1.

Finally, Gate 1 decision evaluates the project using the MAP Project Rating Gate 1 and the MAP Project Charter, producing the Gate 1 decision.

Stage 1 contains no cycles, and all dependencies follow the input-output relationships defined above.