MAP Process Guide – Process Architecture Overview

The MAP Process Guide defines a structured approach for developing and evaluating potential projects. The guide follows a staged process architecture in which the overall process is divided into a sequence of stages. Each stage represents a logical phase in the development and evaluation of a MAP project.

Within each stage, the work is organized into a set of activities. Activities represent the individual steps that must be performed in order to progress through the stage. Each activity clearly specifies the required inputs and the expected outputs. Inputs represent the information, artifacts, or results produced by previous activities that are required before the activity can be executed. Outputs represent the deliverables generated by the activity.

This input–output structure ensures that the process is transparent, traceable, and repeatable. Before an activity can be executed, all required inputs must be available. The activity then transforms these inputs into defined outputs, which may serve as inputs for subsequent activities within the same stage or in later stages of the process.

The outputs generated throughout the process can take the form of reports, structured documents, templates, or other artifacts that capture relevant information about the project. These artifacts support decision making and ensure that knowledge produced during the process is documented and traceable.

At the end of each stage, a gate decision is performed. The gate evaluates the outputs produced during the stage and determines whether the project should proceed to the next stage of the MAP process. Depending on the evaluation outcome, the project may be approved to continue, revised, or rejected.

By structuring the MAP process into stages, activities, inputs, outputs, and gates, the process guide provides a clear framework that supports systematic analysis, informed decision making, and consistent project development.

MAP Process Guide – Stage 1 and Stage 2

Stage 1

Activity 1 — Review Market

Input

Idea description

Output

Market Review report

Activity 2 — Review Portfolio

Input

Idea description.

Output

Portfolio Review report

Activity 3 — Perform Competitive Analysis

Input

Idea description.

Output

Competitor Analysis report

Activity 4 — Analyzing underlying problem/opportunity/threat

Input

Market Review report

Portfolio Review report

Competitor Analysis report

Output

Problem Canvas

Activity 5 — Define Mission, Goals and Objectives

Input

Problem Canvas

Output

Mission One Pager

Activity 6 — Estimate Project Size, Impact and Strategic Fit

Input

Mission One Pager

Output

Project Estimation

Activity 7 — Define High Level Risks

Input

Mission One Pager

Project Estimation

Output

Project Charter

Activity 8 — Estimate resources to MAP project

Input

Mission One Pager

Project Estimation

Output

MAP Resources I (Fields: Type of resources, Resource usage)

Activity 9 — Allocate team members for MAP project

Input

MAP Resources I (Fields: Type of resources, Resource usage)

Output

MAP Resources II (Fields: Ressources allocation)

Activity 10 — Estimate MAP Project Duration

Input

Mission One Pager

Project Estimation

MAP Resources II (Fields: Ressources allocation)

Output

MAP Duration

Activity 11 — ONE PAGER TEMPLATE COMPLETED

Input

Problem Canvas

Mission One Pager

Project Estimation

Output

One Pager Template

Activity 12 — Elaborate MAP Project Charter

Input

Mission One Pager

Project Charter

MAP Resources II (Fields: Ressources allocation), MAP Duration

Output

MAP Project Charter

Activity 13 — Rate MAP project (Stage 1)

Input

One Pager Template

MAP Project Charter

Output

MAP Project Rating Gate 1

Gate 1 — Gate 1 decision

Input

MAP Project Rating Gate 1

MAP Project Charter

Output

Gate 1 decision: Approval for moving to Stage 2 OR Rejection

Stage 2

Activity 1 — Identify Stakeholders

Description

Identify stakeholders involved in or affected by the potential project.

Input: One Pager Template

Output: Stakeholder

Activity 2 — Characterize Persona

Description

Develop personas representing key stakeholder roles and perspectives.

InputStakeholder

Output

Persona

Activity 3 — Elicit Stakeholder Needs

Description

Collect stakeholder needs through interviews, workshops, or discussions.

Input

Stakehoder

Persona

Output

Needs elicitation outcome

Activity 4 — Formulate and document Stakeholder Needs

Description

Structure and document stakeholder needs in a clear and traceable format.

Input

Needs elicitation outcome

Output

Need statement

Owner

Originator

Supporting documentation

Activity 5 — Identify Drivers & Constraints

Description

Identify drivers and constraints influencing the potential project.

Input

One Pager Template

Output

Drivers & Constraints

Activity 6 — Identify Stakeholders related to Drivers&Constraints

Description

Identify stakeholders related to specific drivers and constraints.

Input

Drivers & Constraints

Output

Stakeholder

Activity 7 — Formulate needs related to these Drivers & Constraints and document them

Description

Input

Drivers & Constraints

Stakeholder

Output

*Need Statement

*trace to source

*Originator/Author

*Owner

*Criticality

*Rationale/Reason Why

*Allocation / Budgeting

Gate 2

Description

Gate 2 evaluates the outputs generated during Stage 2 and determines whether the MAP process proceeds to the next stage.

Input

Stage 2 outputs

Output

Gate 2 decision