MAP Process Guide – Stage 1 and Stage 2

Stage 1

Activity 1 — Review Market

Input

Idea description

Output

Market Review report

Activity 2 — Review Portfolio

Input

Idea description.

Output

Portfolio Review report

Activity 3 — Perform Competitive Analysis

Input

Idea description.

Output

Competitor Analysis report

Activity 4 — Analyzing underlying problem/opportunity/threat

Input

Market Review report

Portfolio Review report

Competitor Analysis report

Output

Problem Canvas

Activity 5 — Define Mission, Goals and Objectives

Input

Problem Canvas

Output

Mission One Pager

Activity 6 — Estimate Project Size, Impact and Strategic Fit

Input

Mission One Pager

Output

Project Estimation

Activity 7 — Define High Level Risks

Input

Mission One Pager

Project Estimation

Output

Project Charter

Activity 8 — Estimate resources to MAP project

Input

Mission One Pager

Project Estimation

Output

MAP Resources I (Fields: Type of resources, Resource usage)

Activity 9 — Allocate team members for MAP project

Input

MAP Resources I (Fields: Type of resources, Resource usage)

Output

MAP Resources II (Fields: Ressources allocation)

Activity 10 — Estimate MAP Project Duration

Input

Mission One Pager

Project Estimation

MAP Resources II (Fields: Ressources allocation)

Output

MAP Duration

Activity 11 — ONE PAGER TEMPLATE COMPLETED

Input

Problem Canvas

Mission One Pager

Project Estimation

Output

One Pager Template

Activity 12 — Elaborate MAP Project Charter

Input

Mission One Pager

Project Charter

MAP Resources II (Fields: Ressources allocation), MAP Duration

Output

MAP Project Charter

Activity 13 — Rate MAP project (Stage 1)

Input

One Pager Template

MAP Project Charter

Output

MAP Project Rating Gate 1

Gate 1 — Gate 1 decision

Input

MAP Project Rating Gate 1

MAP Project Charter

Output

Gate 1 decision: Approval for moving to Stage 2 OR Rejection

Stage 2

Activity 1 — Identify Stakeholders

Description

Identify stakeholders involved in or affected by the potential project.

Input: One Pager Template

Output: Stakeholder

Activity 2 — Characterize Persona

Description

Develop personas representing key stakeholder roles and perspectives.

InputStakeholder

Output

Persona

Activity 3 — Elicit Stakeholder Needs

Description

Collect stakeholder needs through interviews, workshops, or discussions.

Input

Stakehoder

Persona

Output

Needs elicitation outcome

Activity 4 — Formulate and document Stakeholder Needs

Description

Structure and document stakeholder needs in a clear and traceable format.

Input

Needs elicitation outcome

Output

Need statement

Owner

Originator

Supporting documentation

Activity 5 — Identify Drivers & Constraints

Description

Identify drivers and constraints influencing the potential project.

Input

One Pager Template

Output

Drivers & Constraints

Activity 6 — Identify Stakeholders related to Drivers&Constraints

Description

Identify stakeholders related to specific drivers and constraints.

Input

Drivers & Constraints

Output

Stakeholder

Activity 7 — Formulate needs related to these Drivers & Constraints and document them

Description

Input

Drivers & Constraints

Stakeholder

Output

*Need Statement

*trace to source

*Originator/Author

*Owner

*Criticality

*Rationale/Reason Why

*Allocation / Budgeting

Gate 2

Description

Gate 2 evaluates the outputs generated during Stage 2 and determines whether the MAP process proceeds to the next stage.

Input

Stage 2 outputs

Output

Gate 2 decision