# MAP Process Guide – Stage 1 Template

# Stage 1

## Activity 1 — Review Market

Description

Review the relevant market environment to understand trends, conditions, and external factors that may influence the potential project.

Input

Project idea / idea description

Output

Market review report

## Activity 2 — Review Portfolio

Description

Review the current portfolio of projects and initiatives to position the potential MAP project within the organizational context.

Input

Project idea / idea description

Output

Portfolio review report

## Activity 3 — Perform Competitive Analysis

Description

Analyze competitors and alternative solutions to understand the competitive landscape related to the project opportunity.

Input

Project idea / idea description

Output

Competitor analysis report

## Activity 4 — Analyzing underlying problem/opportunity/threat

Description

Analyze the underlying problem, opportunity, or threat that motivates the MAP project.

Input

Market review report

Portfolio review report

Competitor analysis report

Output

Problem canvas

## Activity 5 — Define Mission, Goals and Objectives

Description

Define the mission, goals, and objectives of the MAP initiative.

Input

Problem canvas

Output

Mission one pager

## Activity 6 — Estimate Project Size, Impact and Strategic Fit

Description

Estimate the scale of the project, its potential impact, and its strategic relevance within the organization.

Input

Mission one pager

Output

Project estimation

## Activity 7 — Define High Level Risks

Description

Identify major risks associated with the potential project.

Input

Project estimation

Output

List of high-level risks

## Activity 8 — Estimate resources to MAP project

Description

Estimate the resources required to conduct the MAP project.

Input

Risk overview

Output

Resource estimation

## Activity 9 — Allocate team members for MAP project

Description

Allocate team members responsible for conducting the MAP project.

Input

Resource estimation

Output

Resource allocation

## Activity 10 — Estimate MAP Project Duration

Description

Estimate the duration required to complete the MAP project activities.

Input

Resource allocation

Output

MAP project duration estimation

## Activity 11 — ONE PAGER TEMPLATE COMPLETED

Description

Complete the MAP One Pager template summarizing the project concept.

Input

MAP project duration estimation

Output

Completed MAP One Pager

## Activity 12 — Elaborate MAP Project Charter

Description

Prepare the MAP Project Charter defining the scope and objectives of the MAP project.

Input

MAP One Pager

Output

MAP Project Charter

## Activity 13 — Rate MAP project (Stage 1)

Description

Evaluate and rate the MAP project based on the information gathered during Stage 1.

Input

MAP Project Charter

Output

MAP project rating

# Gate 1 — Gate 1 decision

Description

Gate 1 evaluates the MAP project based on the outputs generated during Stage 1.

Input

MAP project rating

MAP Project Charter

Output

Gate 1 decision