MAP Process Guide

MAP Process Architecture

The MAP framework structures the early phases of project definition into a sequence of stages separated by decision gates. Each stage contains a series of structured steps that progressively transform an initial project idea into a clearly defined project proposal.

Within each step, specific inputs, activities, and outputs are defined. In some cases, a step may contain several analysis activities that can be conducted in parallel. The outputs generated in each step become the inputs for subsequent steps and ultimately support the decision taken at the corresponding gate.

Stage 1 — Strategic Context and Project Framing

Stage 1 transforms an initial project idea into a structured project framing. During this stage, the project team analyzes the external and internal context, clarifies the project motivation, and prepares the documentation required for the Gate 1 evaluation.

Step 1 — Conduct Market Research

Input: Initial project idea / idea description

| Activity | Purpose | Output |
| --- | --- | --- |
| Review market | Assess market trends and environment | Market review report |
| Review portfolio | Position the project within existing initiatives | Portfolio review report |
| Perform competitive analysis | Understand competitors and alternative solutions | Competitor analysis report |

Step 2 — Analyze the Underlying Problem, Opportunity or Threat

Inputs: Market review report, Portfolio review report, Competitor analysis report

Activity: Analyze the underlying problem, opportunity, or threat motivating the project.

Output: Problem canvas

Step 3 — Define Mission, Goals and Objectives

Input: Problem canvas

Activity: Define the mission, goals, and objectives of the project.

Output: Mission one pager

Step 4 — Assess Project Size, Impact and Strategic Fit

Input: Mission one pager

Activity: Estimate project scale, expected impact, and strategic relevance.

Output: Project estimation

Step 5 — Identify High-Level Risks

Input: Project estimation

Activity: Identify major risks associated with the potential project.

Output: List of major risks

Step 6 — Plan the MAP Project Setup

Input: List of major risks

| Activity | Purpose | Output |
| --- | --- | --- |
| Estimate MAP project resources | Determine required resources | Resource estimation |
| Allocate MAP team members | Assign responsible team members | Resource allocation |
| Estimate MAP project duration | Define timeline for MAP activities | MAP lead time |

Step 7 — Prepare MAP Framing Documents

Inputs: Resource estimation, Resource allocation, MAP lead time

| Activity | Purpose | Output |
| --- | --- | --- |
| Complete MAP One Pager | Summarize the project concept | MAP One Pager |
| Elaborate MAP Project Charter | Define scope and objectives of MAP initiative | MAP Project Charter |
| Rate the MAP project | Evaluate the project for gate decision | MAP project rating |

Gate 1 — MAP Project Evaluation

Gate 1 represents the decision point between Stage 1 and Stage 2. The project is evaluated based on the results generated during Stage 1.

Inputs: MAP Project Charter, MAP project rating, Stage 1 outputs

Possible decisions: Proceed to Stage 2 / Revise / Stop

Output: Gate 1 decision

Stage 2 — Stakeholder and Needs Analysis

Stage 2 focuses on identifying stakeholders and understanding their needs, expectations, and constraints related to the potential project.

Step 1 — Identify and Characterize Stakeholders

| Activity | Purpose | Output |
| --- | --- | --- |
| Identify stakeholders | Determine actors involved in or affected by the project | Stakeholder list |
| Characterize personas | Represent key stakeholder roles | Persona profiles |

Step 2 — Elicit and Document Stakeholder Needs

| Activity | Purpose | Output |
| --- | --- | --- |
| Elicit stakeholder needs | Collect needs through interviews/workshops | Needs elicitation outcome |
| Formulate and document stakeholder needs | Structure stakeholder needs | Need statements |

Step 3 — Analyze Drivers and Constraints

| Activity | Purpose | Output |
| --- | --- | --- |
| Identify drivers and constraints | Determine influencing factors | Drivers and constraints list |
| Map stakeholders related to drivers and constraints | Link stakeholders to these factors | Stakeholder mapping |

Gate 2 — (...)

Gate 2 evaluates the results of the stakeholder and needs analysis.

Stage 3 — (...)

Further project analysis and definition activities take place.